## Folha1
Sprint BurnDownChart
Task ID | Task Description | Estimate | 2022-10-19 | 2022-10-20 | 2022-10-21
|  | 0 | 1 | 2 | 3
1 | Set up workspace | 1 | 0.5
2 | Organise project structure | 1 | 0.5
3 | Find design patterns | 2
4 | Find code smells | 2
5 | Submit | 1
6
7
8
9
10
Completed effort |  | 0 | 1 | 0 | 0
Remaining effort |  | 7 | 6 | 6 | 6
Ideal Burndown |  | 7 | 4.6667 | 2.3333 | 0