## Folha1
Sprint Backlog
Task ID | Description | TODO |  |  | In progress |  | Reviewing |  | Done
|  | date added | date completed | Done by | date added | date completed | date added | date completed | date added | date completed
1 | Reunião de divisao de trabalho | 2022-11-10 | 2022-11-10 | Nádia Mendes João Esteves |  |  |  |  | 2022-11-10 | 2022-11-10
2 | Reunião de trabalho para a distribuicao das tarefas | 2022-11-13 | 2022-11-13 | Nádia Mendes João Esteves Jóse Morgado |  |  |  |  | 2022-11-13 | 2022-11-13
3 | Reunião sobre implementação direta do sprint 1 | 2022-11-19 | 2022-11-19 | Nádia Mendes João Esteves Jóse Morgado |  |  |  |  | 2022-11-19 | 2022-11-19
4 | realização use case diagram | 2022-10-19 | 2011-11-03 | Nádia Mendes João Esteves Jóse Morgado |  |  |  |  | 2022-11-22 | 2011-11-03
5 | realizacao use case descriptions | 2022-11-22 | 2011-11-03 | Nádia Mendes João Esteves Jóse Morgado |  |  |  |  | 2022-11-22 | 2011-11-03
6 | realizacao user storys | 2022-11-23 | 2011-11-03 | Nádia Mendes João Esteves Jóse Morgado |  |  |  |  | 2022-11-23 | 2011-11-03
7 | Alteracao do codigo | 2022-11-24 | 2022-11-01 | NádiaMendes |  |  |  |  | 2022-11-24 | 2022-11-01
8 | criacao de testes unitarios | 2022-11-29 | 2022-11-29 | NádiaMendes |  |  |  |  | 2022-11-29 | 2022-11-29
9 | analise das metricas | 2022-11-02 | 2022-11-02 | NádiaMendes |  |  |  |  | 2022-11-02 | 2022-11-02
10 | criação do video | 2022-11-03 | 2022-11-03 | NádiaMendes |  |  |  |  | 2022-11-03 | 2022-11-03
11 | elaboração do relatorio final | 2022-11-04 | 2022-11-04 | NádiaMendes |  |  |  |  | 2022-11-04 | 2022-11-04